## Demobilize
[Your company name here] Site Shutdown Checklist
Work Area:
Contact Number:
Superintendent:
Contact Number:
Project Executive:
ITEM | DESCRIPTION | IS THIS ITEM CONSIDERED SAFE / SECURE | RESPONSIBILITY | INITIAL | COMMENTS
WORK AREA INSPECTION ITEMS
1 | Relieve any MEP systems that are under pressure for testing.
2 | Ensure Fire Hydrant is charged
3 | Direct specialty contractors to remove and loose debris from roof / balconies / areas without façade installed and secure in a location not affected by a wind or seismic event
4 | Inspect perimeter railings at the roof / balcony areas (any area without the permanent railing, or façade installed)
5 | Inspect floors/storage areas, identify and remove trash, debris and other fire hazards
6 | Take video/photos of every floor, documenting status of work, and stored materials
7 | Ensure all lunch/break areas are cleaned and trash cans are emptied
8 | Check all penetrations; ensure they are correctly covered, secured and labelled
9 | Check that emergency egress signage is visible and in position
10 | Check that Emergency Egress paths are identified, clear of materials, and have temporary lighting
11 | Check that all flammable items including, but not limited to, fuel, gas, oxygen, propane is secured and stored correctly or removed from site
PRECINCT OPERATIONS - UTILITIES
12 | Field team to discuss any additional 'make safe' electrical actions
13 | Confirm that all temp emergency lighting is operational
14 | Inspect the site perimeter to ensure compliance with SW PPP. Ensure that fencing encircles any retention ponds.
15 | Clean all temp toilets and cut off water, if provided
16 | Confirm with fire protection contractor that the fire standpipe is operational, and verify the fire pump room keys are accessible.
17 | Verify that the fire alarm is operational
PRECINCT OPERATIONS - SITE SECURITY
18 | Inspect site perimeter to ensure fencing is secured
19 | Purchase new locks for gates and turnstyles. Secure all access points. Chain up turnstyles, if applicable.
20
21 | Verify that site security (Mgt and site team) have all necessary company contacts
22 | Increase site security resource for 2 days following suspension. Increase day shift security to align with 2nd and 3rd shifts.
CRANES AND OTHER SUSPENDED EQUIPMENT
1 | Inspect tower crane enclosures | N/A
2 | Ensure tower cranes are free to "weathervane". De-energize control panel | N/A
3 | Crane supervisor must inspect and confirm crane(s) are safe / secure | N/A
4 | Man and material hoists to be brought to ground and gates chained (no different to any other day). | N/A
5 | All swing stages to be lowered to the ground and secured. Power to stages reviewed with electrical contractor for disconnection | N/A
N/A
N/A
OTHER
1 | Ensure all planned deliveries are cancelled
1 | Review / adjust site security assignments
1 | Specialty contractors should collect / secure equipment and tools
|  | WORK AREA | RESPONSIBILITY